## Sheet1
| Course Semester |  |  |  |  | End of Semester | Outside course semester
| 2021-10-17 | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2021-01-02 | 2021-01-09 | 2021-01-16 | 2021-01-23 | 2021-01-30
| Week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | Week 13 | week 14 | week 15 | weel 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22
Project timeline
Assignm-ent timeline
| 2021-10-17 | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2021-01-02 | 2021-01-09 | 2021-01-16 | 2021-01-23 | 2021-01-30
| Week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | Week 13 | week 14 | week 15 | weel 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22
List out functionalities of stockIT for development. Research and brainstorm tools/tech/skills required for full development.
Brainstorm coding languages to be used. Discuss and practice with MIT App creator. Discuss feedback from our experiences with both.
Discuss what further artifacts or deliverables could be implemented.
Define deliverable(s) for stockIT project. Transition to Figma for wireframing and prototyping. Figma mobile app and web browser application wireframing begins
Discuss Jobs/Roles required to see project through to fruition/Marketable product.
Identify and discuss the risks in the project - how can they be mitigated, reduced or managed.
Work continues on Figma wireframing and creating design assets for UX/UI elements.
Implement risk management program. Scale delvierables to suit risk mitigation plan.
Break down assignment segments. Assign tasks to Group Members. New GitHub repo, teams channel and groups. Organise meeting schedules. Assignment 2 - what our thoughts are.
Discuss ideas surrounding Asgn 5 presentation requirements. Allocate team leaders for Asgn 5. Tasks fully allocated for Asgn 3.
Tools&Tech reporting research begins. Plans&Progress reporting begins. Jobs,Roles reporting begins.
Assignment 5 Storyboarding and Scripting due. Draft video and script presented to group members by Asgn 5 project leaders.
Discuss Feedback from asgn2 and incorporate into asgn3