## Sheet1
Timeline and Timeframe Assignments 3 & 5
| Course Semester |  |  |  |  | End of Semester | Outside course semester
| 2021-10-17 | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2021-01-02 | 2021-01-09 | 2021-01-16 | 2021-01-23 |  | 2021-01-30
| Week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | Week 13 | week 14 | week 15 | weel 16 | week 17 | week 18 | week 19 | week 20 | week 21 |  | week 22
project
assignment
Task & Hours breakdowns
| Task |  | Area |  | Time allocated (hrs) | Project Leaders | [7 empty] | Group Member |  | Assigned Hrs
| Group Process |  | Team profile |  | 3.6 | Taylen | [7 empty] | Taylen |  | 0
| Career plans |  |  |  | 3.6 | Taylen | [7 empty] | Ahmet |  | 0
| GitHub organisation |  | Tools |  | 1.8 | Taylen | [7 empty] | Tetsu |  | 0
| Additional Tools/MS Teams/ETC |  |  |  | 1.8 | Taylen | [7 empty] | Hugo |  | 7.5
| Report on Efficacy of tools |  |  |  | 3.6 | Taylen | [7 empty] | Tim |  | 45
| Overview |  | Project Plan |  | 4 | [8 empty] | Brandon |  | 0
| Aims |  | Project Plan |  | 68 | Tim
| Plans and Progress |  |  |  |  | Tim
| Roles |  |  |  |  | Hugo
| Scopes and Limits |  |  |  |  | Tim
| Tools and Technologies |  |  |  |  | Ahmet
| Testing |  |  |  |  | Tim
| Timeframe |  |  |  |  | Tim
| Risks |  |  |  |  | Tim
| Group Process & Comms |  |  |  |  | Taylen
| Analysis of Jobs to Perform |  | Skills & Jobs |  | 2 | Hugo
| Job Advertisement #1 |  | Skills & Jobs |  | 4.9 | Hugo
| Job Advertisement #2 |  |  |  | 4.9 | Hugo
| Job Advertisement #3 |  |  |  | 4.9 | Hugo
| Job Advertisement #4 |  |  |  | 4.9 | Hugo
| Feedback |  | Group |  | 1.8 | Group
| Group Reflection |  | Group |  | 1.8 | Group
| PDF Report |  | Presentation |  | 7.2 | Taylen
| Website |  |  |  | 7.25 | Taylen
| Storyboard |  | Assignment 5 |  | 14.4 | Brandon & Tetsu
| Script |  |  |  | 28.8 | Brandon & Tetsu
| Video |  |  |  | 28.8 | Brandon & Tetsu
| Total Hours |  |  |  | 198.05
| Total hours per person |  |  |  | 33.0083
Brainstorm coding languages to be used. Discuss and practice with MIT App creator. Discuss feedback from our experiences with both.
List out functionalities of stockIT for development. Research and brainstorm tools/tech/skills required for development
Break down assignment segments. Assign tasks to Group Members. New GitHub repo, teams channel and groups. Organise meeting schedules. Assignment 2 - what our thoughts are.
Tools&Tech reporting research begins. Plans&Progress reporting begins. Jobs,Roles reporting begins.
Work continues on Figma wireframing.